## Start Here
HER WELLNESS HARMONY — UAT 1a (Batch 1 retest)
Sheila — this workbook retests only what Batch 1 fixed.
Same columns as UAT 1, plus Your UAT 1 Note so each row opens with your words.
HOW TO USE
1. Use the non-admin member account and the fresh unassessed account we hand you (credentials separate).
2. Work the phase tabs in order. Mark Pass / Fail / Partial. Add notes.
3. Do not retest the whole of UAT 1. Anything still pending is on the Not In This Round tab.
BEFORE YOU START
- Existing unpaid test accounts may no longer show a Restoration badge. That is intended (row Phase 3 / 1.2).
- About a third of Batch 1 is foundation work you cannot see on screen (database hygiene, identity checks). It is listed on Not In This Round as untestable, not as unfinished.
WHAT DECIDES THIS BATCH
If Phase 2 / 5.2 (mild scoring), Phase 2 / 5.3 (members see lessons), and Phase 3 / 1.2 (badge tells the truth) all Pass, Batch 1 succeeded even if a cosmetic row fails.

## Phase 1 – Studio
Section | Step | Your UAT 1 Note | What To Do | What You Should See | Pass / Fail | Your Notes
1 | 6 | There is also the member content editor and the weekly notes editor in the portal studio | Look at Portal Studio section in sidebar | You see Portal Script Generator, Portal Video Library, Member Content Editor, and Weekly Notes Editor

## Phase 2 – Assessment
Section | Step | Your UAT 1 Note | What To Do | What You Should See | Pass / Fail | Your Notes
1 | 3 | No sign out button is available | On the sidebar, find Account and Sign Out at the bottom. Click the word Account, then Sign Out | Account is clickable even with no avatar image. Sign Out is labelled and returns you to the main site
3 | 3 | It does navigate to guided pathways | After assessment, click View My Roadmap or open My Guided Roadmap in the sidebar | The menu and page read My Guided Roadmap, not Guided Pathways
3 | 4 | Could not reach View Tiers / upgrade after assessment | After completing the assessment, open Deep Support Coaching from the sidebar | Membership options appear. Before the assessment, that menu item is not shown
4 | 1 | The awareness tier view is showing the user account at the restoration level | As admin, set Preview As to Awareness | Content is filtered to Awareness. No Restoration badge or Restoration-only features
4 | 3 | When I view as a tier member, the portal studio and social studio are still visible | While Preview As is set to any member tier, look at the sidebar | Social Studio and Portal Studio are gone. Exit preview restores them
5 | 2 | I listed all of the symptoms as mild (between 7-10) and patterns still came back medium to high / Integration | On a fresh unassessed account, complete the assessment with mild ratings (7–10) throughout | Recommended tier is Awareness or Foundation, not Integration. Pattern cards are labelled low, not medium or high
5 | 3 | The only account that is able to see any lessons in the guided pathways, is the admin account | Sign in on the non-admin member account and open My Guided Roadmap | Published lessons are visible. You are not looking at an empty page

## Phase 3 – Delivery
Section | Step | Your UAT 1 Note | What To Do | What You Should See | Pass / Fail | Your Notes
0 | 1 | There needs to be the Deep Support item | On a post-assessment account, count the sidebar items | Deep Support Coaching is present and opens membership options
1 | 2 | It isn't showing the correct tier badge, it always shows the restoration tier even with a free account | Open an unpaid test account with no payment history | No Restoration badge. No membership tier claimed anywhere
2 | 1 | The name Guided Pathways isn't correct, the item listed in the left menu needs to be named My Guided Roadmap | Look at the sidebar label for the roadmap | It reads My Guided Roadmap
2 | 2 | This is a PASS for the admin account, but it FAILS for all other users | On the non-admin member account, open My Guided Roadmap | Lessons appear for the member, not only for admin
4 | 1 | This only works for the admin account and not the user accounts | On the non-admin member account, open My Progress | Progress content appears rather than an empty or broken page
6 | 3 | There is no option to view as a free account (no tier) in the admin account | As admin, open Preview As and choose Free account (no tier) | Gated content is locked. You can test locked screens without a second login
7 | 3 | Counter shows 150 regardless of tier level that is being previewed | Preview As Awareness, then open Ask the HWH Coach and check the monthly limit | The counter matches the previewed tier (Awareness is 10), not a flat 150
8 | 1 | The trial button does open a stripe checkout. But the trial isn't free, it is $19 | Open Deep Support Coaching and read the trial button | The button names the real price: Start 21-Day Trial, $19 (not Start Free Trial)
9 | 1 | The member content editor page is blank | As admin, open Portal Studio > Member Content Editor | The page loads. You can draft and save a post
9 | 2 | Can't publish, see above response | Publish a Member Content article, then open Member Content as a member (or Preview As) | The published article is visible to a member who has access
9 | 3 | Can't test | Publish an article gated above Awareness. Preview As Awareness | The article is hidden at Awareness and visible at a higher preview tier
9 | 4 | The weekly Notes editor page is blank | As admin, open Portal Studio > Weekly Notes Editor | The page loads. You can draft and save a note
9 | 5 | Can't publish, see above response | Publish a Weekly Note, then open Weekly Notes as a member | The published note is visible
9 | 6 | Can't test | Publish a note gated above Foundation. Preview As Foundation vs Guided | Visibility follows the tier gate
9 | 7 | Can't test | In Member Content Editor, use Draft with AI if available, then save | A draft is produced and can be saved without a blank page
10 | 2 | The tier badge doesn't match the correct tier | On an unpaid account, open Account | No paid tier is claimed. Recommendation, if any, is not shown as membership
10 | 3 | This opens in the same tab, not a new tab | Click Manage Billing (on an account that has a Stripe customer). Stop at the Stripe page; do not change plans | Stripe opens in a new tab. The portal tab stays open

## Phase 5 – Trial & Billing
Section | Step | Your UAT 1 Note | What To Do | What You Should See | Pass / Fail | Your Notes
1 | 1 | The coaching (Deep Support Coaching) item is missing in the menu | After assessment, open Deep Support Coaching from the sidebar | The membership / tier page opens
1 | 2 | Doesn't open in new tab | Click Start 21-Day Trial, $19 on any tier card. Stop at Stripe Checkout; do not pay (paying is Batch 2) | Checkout opens in a new tab

## Not In This Round
UAT 1 ref | Your note (summary) | Why not in 1a | When
Phase 1 / 5.3 | Green vs blue strength card border | Cosmetic; no code change unless you ask for blue | On request
Phase 1 / 1.8, 5.7, 5.8 | Script Generator pain points, saved script access, copy flow | Batch 4 content studio work | UAT 4a
Phase 2 / 3.5, 3.6, 3.7 | Pattern Library, Start Here, Dashboard results mismatch | Batch 3 clinical results work | UAT 3a
Phase 2 / 5.1 | Dashboard focus vs roadmap order (gut-first) | Batch 3; severity labels are fixed in 1a, ordering is not | UAT 3a
Phase 3 / 3.1, 3.2 | Scripts only on NS-01 | Content + Batch 4 saved-script access | UAT 4a
Phase 3 / 7.4, 7.10 | AI Coach relevance and long dashes | Batch 4 | UAT 4a
Phase 5 / payment rows | Checkout lands wrong tier, trial end date, plan change, cancel, day 18/19/21 emails | Batch 2 money and journey emails | UAT 2a
Phase 6 / 4.3 | day_11_mini_assessment vs _reminder | Two intentional events; explanation only | No code
— | Migration hygiene, Clerk identity binding, lifecycle webhooks, price audit | Foundation work; no on-screen test | Untestable by design