## Start Here
HER WELLNESS HARMONY — Member Portal UAT Test Workbook
Welcome Sheila! This workbook contains all the test guides for the HWH member portal.
Each tab is a separate phase of the portal. Work through them in order.
HOW TO USE THIS WORKBOOK
1. Start with Phase 1 (Portal Studio) — this tests the admin/content side you already know.
2. Move to Phase 2 (Assessment) — test the wellness assessment wizard and results.
3. Phase 3 (Delivery) is the big one — all member-facing features including AI Coach, lessons, symptom log, priority support.
4. Phase 5 (Trial & Billing) — test the Stripe checkout, trial journey, and tier changes.
5. Phase 6 (MailerLite) — verify the MailerLite groups, triggers, and automations.
FOR EACH TEST STEP
• Read the 'What To Do' column and follow the instruction.
• Compare what you see on screen to the 'What You Should See' column.
• Mark the 'Pass / Fail' column: Pass, Fail, Partial, or Skipped.
• Use the 'Your Notes' column to write any comments, issues, or suggestions.
PORTAL URL
https://instant-site-move.vercel.app/portal
LOGIN
Sign in with your admin account (support@herwellnessharmony.com).
For fresh-account tests, sign out and create a new account with a different email.
STRIPE TEST CARD (for Phase 5)
Card: 4242 4242 4242 4242 ¦ Expiry: any future date ¦ CVC: any 3 digits ¦ ZIP: any 5 digits
QUESTIONS OR ISSUES?
If something doesn't work or you're unsure, write it in the 'Your Notes' column and keep going.
If you're stuck and can't proceed, note which Phase/Section/Step and send the workbook back.
TABS IN THIS WORKBOOK
• Phase 1 – Studio
• Phase 2 – Assessment
• Phase 3 – Delivery
• Phase 5 – Trial & Billing
• Phase 6 – MailerLite

## Phase 1 – Studio
Section | Step | What To Do | What You Should See | Pass / Fail | Your Notes
SECTION 1: Your Content Studio Now Has Two Workspaces
1 | 1 | Go to instant-site-move.vercel.app and sign in | You see the portal dashboard with your sidebar navigation | Pass
1 | 2 | Look at the left sidebar under your admin navigation | You see TWO studio sections: 'Social Studio' and 'Portal Studio' (not one 'Content Studio') | Pass
1 | 3 | Click on 'Social Studio' section header | Opens the Social Studio dashboard — title says 'Social Studio' (not 'Content Studio') | Pass
1 | 4 | Look at Social Studio sub-items in sidebar | You see: Script Generator, Content Library, Content Calendar, Campaigns — same as before | Pass
1 | 5 | Click on Content Library under Social Studio | Opens your social content library — NO 'Publish to Portal' option in the ••• menu of any item | Pass
1 | 6 | Look at Portal Studio section in sidebar | You see: Portal Script Generator, Portal Video Library | Partial | There is also the member content editor and the weekly notes editor in the portal studio but when you click on them, there page is blank.
1 | 7 | Check member navigation (below the studio sections) | 'Community' link is NOT visible in the sidebar | Pass
1 | 8 | Click on Social Studio > Script Generator | Your existing social script generator works normally — no changes | Fail | The pain points and false beliefs for each pillar are not correct. It gives the same default choices for every pillar instead of the customized choices for each pillar. The hook types are also not correct. The hook types are supposed to be Pattern Disruption, Hidden Driver, Misinterpretation, and Unexpected Connection. This could possibly need another MD file.
SECTION 2: Browsing Your Video Catalog
2 | 1 | Click on 'Portal Video Library' in the sidebar | Opens the Portal Video Library page. You see a header: 'Portal Video Library' with a count like '0 of 148 published' | Pass
2 | 2 | Scroll through the video list | You see all 148 videos organized by sub-category (e.g. 'Introduction to Gut Health', 'Gut Lining Permeability', etc.) | Pass
2 | 3 | Use the Phase dropdown filter — select 'Gut Function' | Only Gut Function videos are shown (49 videos across 6 sub-categories) | Pass
2 | 4 | Use the Phase dropdown filter — select 'Nervous System Foundation' | Only the 15 NS-xx videos are shown | Pass
2 | 5 | Use the Status dropdown filter — select 'Not Started' | All 148 videos shown (none have been scripted yet) | Pass
2 | 6 | Type 'gut lining' in the search box | Only videos with 'gut lining' in the title or code are shown | Pass
2 | 7 | Clear all filters | Full list of 148 videos visible again | Pass
SECTION 3: Uploading Videos and Changing Status
3 | 1 | Find video GL-01 in the list. Click the ••• menu | You see options: Edit Details, Add Video, Mark Scripted/Recorded/Uploaded/Published, Delete | Pass
3 | 2 | Click 'Add Video' from the ••• menu | A dialog opens with two tabs: 'Paste URL' and 'Upload File' | Pass
3 | 3 | In the Paste URL tab, enter any test URL (e.g. https://example.com/test.mp4) and click Save | URL saves. Video now shows an orange 'Video' badge next to its status | Pass
3 | 4 | Click the ••• menu on GL-01 again and choose 'Mark Scripted' | Status badge changes from 'Not Started' to 'Scripted' (yellow) | Pass
3 | 5 | Change status to 'Recorded' then 'Uploaded' then 'Published' | Status badge changes through each state. When Published, badge turns green. | Pass
3 | 6 | Filter by Status = 'Published' | Only GL-01 appears | Pass
3 | 7 | Change GL-01 back to 'Not Started' using the ••• menu | Status resets to gray 'Not Started' | Pass
SECTION 4: Adding and Editing Videos
4 | 1 | Click the 'Add Video' button (top right of the page) | A dialog opens with fields: Video Code, Title, Phase, Sub-Category | Pass
4 | 2 | Enter: Code='TEST-01', Title='My Test Video', Phase='Gut Function', Sub-Category='Test Category'. Click Add. | Video appears in the catalog. Total count increases to 149. | Pass
4 | 3 | Find TEST-01 in the list. Click ••• > Edit Details | Edit dialog shows current title and sub-category | Pass
4 | 4 | Change the title to 'My Updated Test Video' and click Save | Title updates in the list. Reload the page — change persists. | Pass
4 | 5 | Click ••• > Delete on TEST-01 | Video is removed from the catalog. Total goes back to 148. | Pass
SECTION 5: Generating Lesson Scripts
5 | 1 | Click on 'Portal Script Generator' in the sidebar (or use the 'Generate Script' button on the Video Library page) | Opens the Portal Script Generator page. You see 'Primary strength: Command (locked)' | Pass
5 | 2 | In the video list, search for GL-01 and click to select it | GL-01 is highlighted. Below the list it shows: 'Selected: GL-01 — What Is the Gut Lining...' with phase and sub-category | Pass
5 | 3 | Choose 'Analytical' as the secondary strength (should already be selected by default) | Analytical card is highlighted with a blue border | Fail | The border is green, not blue. But I don't know if the color is significant for any particular reason.
5 | 4 | Click 'Generate Script' | Loading spinner appears. After 15-30 seconds, the full script appears below with 6 expandable sections. | Pass
5 | 5 | Review the generated script sections | You see: Learning Objective, Introduction, Core Educational Content, Practical Application, GMH Cascade Connection, Transition — each with content specific to gut lining | Pass
5 | 6 | Scroll down past the 6 sections | You see Action Items (checklist format) and possibly a Reflection Prompt (in an amber box). At the bottom: a legal disclaimer. | Pass
5 | 7 | Click 'Save Script' | Toast message: 'Script saved'. Video GL-01 status should flip to 'Scripted' if it was 'Not Started'. | Partial | I received the message that the script was saved, but I have no way to access the saved script. Status updates to "scripted" correctly.
5 | 8 | Click 'Copy' to copy the full script | Script text copies to your clipboard. Paste it somewhere (Notes, Word) to verify it includes all sections. | Partial | There is the option to copy the script and paste it somewhere else. But that is not a streamlined process. It would be nice if there was some type of script dashboard to have all of my deliverables in one spot. When I upload the video and then ultimately push the content to get scheduled to my social media platforms. This may need a separate MD file.
SECTION 6: Verifying Scripts are Saved
6 | 1 | Go back to Portal Video Library | GL-01 now shows status 'Scripted' (yellow badge) | Pass
6 | 2 | Go back to Portal Script Generator, select GL-01 again | You can generate a new script for it (the old one will be overwritten when you save) | Pass
6 | 3 | Select a different video (NS-01) and choose 'Relator' as secondary strength | NS-01 is selected, Relator card is highlighted | Pass
6 | 4 | Click Generate Script | A new script generates — tone should be warmer/more personal compared to the Analytical version | Pass
6 | 5 | Click Save Script | Toast: 'Script saved'. NS-01 status flips to 'Scripted' in the video library. | Pass
GENERAL FEEDBACK
|  | What was confusing or hard to find? |  |  | Can't find where the saved scripts live. I'm not sure if those are stored somewhere, maybe supabase.
|  | What would make this easier to use? |  |  | It would be easier if I didn't have to copy the script and save it somewhere else to manage later. It would be easier if the entire script was written as a full paragraph instead of sectioning out each part of the script. When you click on the "Guided Pathways" in the left menu, it brings you to the "My Guided Roadmap". My Guided Roadmpa is the correct naming and the Guided Pathways name in the left menu needs to be updated to My Guided Roadmap.
|  | Any errors or unexpected behavior? |  |  | The full list of pain points and false beliefs from the HWH_Pain_Points_False_Beliefs_Master-2 MD file aren't showing in the social script generator. The gallup matrix and the hook styles also are not correct for the social script generator. This may require an updated MD file.
|  | Overall: is this ready for you to start scripting your 148 videos? |  |  | Not yet

## Phase 2 – Assessment
Section | Step | What To Do | What You Should See | Pass / Fail | Your Notes
PHASE 2: Wellness Assessment — Test Guide for Sheila
NOTE: Use a fresh test member account (or create a new sign-up) so baseline ratings use the current 29-item checklist. Old test data from before July 2026 may show fewer comparison columns.
SECTION 1: Login and Getting Started
1 | 1 | Open https://instant-site-move.vercel.app/portal in your browser | Login page appears (Clerk sign-in) | Pass
1 | 2 | Sign in with your admin account (support@herwellnessharmony.com) | You land on the member dashboard | Pass
1 | 3 | To test with a FRESH account: click Sign Out → Sign Up → use a different email address. This ensures clean assessment data. | New account created — you land on the dashboard with no prior assessment | Fail | No sign out button is available
1 | 4 | If you have NOT completed the assessment yet | You see a prominent card: 'Complete Your Wellness Assessment' with a Start Assessment button | Pass
1 | 5 | Click 'Start Here' in the sidebar | Page explains the ~30 minute assessment. Copy does NOT say 'AI-powered.' | Pass
1 | 6 | As admin: use the 'Preview As' dropdown in the sidebar | You can switch between Admin view and member tier previews (Awareness / Foundation / etc.) | Pass | There is the option to switch between the different views but nothing changes when you switch to the different views.
SECTION 2: Wellness Assessment Wizard (13 Steps)
2 | 1 | Click 'Start Assessment' (or go to /portal/intake) | Step 1 of 13: About You and Your Goals. Progress bar shows 1/13. | Pass
2 | 2 | Complete Step 1 and click Next | Step 2: Medical History shows a multi-select checklist (IBS / PMOS / Endometriosis / etc.) plus Other text field. PMOS label appears (not PCOS). | Pass | For the medical history when it asks about pregnancies, deliveries and miscarriages, do not allow the number to be negative.
2 | 3 | Complete Step 2 and click Next through Steps 3-4 | Step 3: Medications — asks about current medications and supplements. Step 4: Family History uses same checklist format. PMOS label appears (not PCOS). | Pass | On this page, it asks about past symptoms and current symptoms. Those sections need to be swapped. Ask about current symptoms first, then ask about history. Ideally, if the symptom is a cuurent symptom, then it shouldn't be an option on the past symptoms list.
2 | 4 | Try clicking Back on Step 3 | You return to Step 2 with your answers preserved. Progress bar updates. | Pass
2 | 5 | Navigate forward again to Step 5: Symptom Inventory | You can select symptoms with frequency (Daily / Weekly / etc.) across 8 categories: Gut Health / Energy & Fatigue / Hormonal / Nervous System / Brain & Cognitive / Metabolic / Immune & Inflammatory / Overall Wellbeing | Pass | Step 5 is Early Life and Birth History. Symptom Inventory is step 6.
2 | 6 | Complete Steps 6-12 (Diet / Sleep / Stress / Movement / Environment / Labs) | Each step saves as you navigate forward and back. No errors. | Pass | This is steps 7-12
2 | 7 | On Step 13: Day 1 Baseline Ratings | You see 29 rating sliders across 6 categories: Gut Health / Energy / Hormonal / Nervous System / Brain / Overall Wellbeing. Scale 1=Severe → 10=None. | Pass
2 | 8 | On Step 13 scroll to open text and consent | Three open text fields plus consent checkbox. Submit is blocked until consent is checked. | Pass
2 | 9 | ERROR TEST: Try clicking Submit WITHOUT checking the consent checkbox | Submit button is disabled or shows an error — you cannot submit without consent | Pass
SECTION 3: Submit and Results
3 | 1 | Check consent and click Submit Assessment | Loading then redirect to Results page. No error toast. | Pass
3 | 2 | On Results page read your pattern summary | You see ATM reasoning / primary and secondary focus / and a tier recommendation with explanation | Pass
3 | 3 | Click 'View My Roadmap' or equivalent CTA | Navigates to Guided Pathways with your personalized roadmap | Partial | It does navigate to guided pathways
3 | 4 | Click 'View Tiers' or upgrade CTA | Opens /portal/coaching with tier options and $19 trial | Fail
3 | 5 | Go to the Pattern Library page (sidebar → Pattern Library) | You see cards for the wellness patterns identified from your assessment. Each card links to a detail page. | Fail | There are cards for the wellness patterns but they aren't the correct cards based on how the wellness assessment was completed. It looks like the cards are default across all accounts instead of being customized.
3 | 6 | Go to Start Here page after completing the assessment | Start Here now reflects your assessment results and journey context instead of the pre-assessment intro | Fail | No assessment results are showing for the fresh account. I am able to see what day I am on when I am logged into the admin account, but nothing is viewable from the fresh account for a user.
3 | 7 | Go to Dashboard | Dashboard shows your top patterns or a summary widget with assessment highlights | Fail | The dashboard doesn't display the assessment results correctly for the fresh account or the admin account. For the admin account it is showing the currect focus as following: Primary is metabolic dysfunction, secondary is gut integrity and motility and a watch area of HPA axis and stress hormone patterns. Yet, the "My Guided Roadmap is showing Gut function -> Metabolic repair -> Hormonal balancing. For the fresh account, it is showing a primary focus of gut restoration, secondary focus of estrogen dominance and hormonal clearance and a watch area of thyroid and metabolic function. But the guided roadmap is showing gut function -> metabolic repair -> hormonal balancing. Those two things within the dashboard are not matching. We did say that gut function is the starting point if the gut integrity is impacting the metabolism and hormones. However, the primary focus shouldn't be metabolism if there are gut issues present. Current focus areas and guided roadmap are not in agreement.
SECTION 4: Admin Preview As (Tier Differences)
4 | 1 | As admin set 'Preview As' to Awareness tier | Browse portal — awareness members see limited lesson features (no action items on lessons) | Fail | The awareness tier view is showing the user account at the restoration level.
4 | 2 | Set Preview As to Foundation tier | Lesson pages show action items and reflection fields | Partial | The lesson for NS-01 is the only lesson that shows the lesson script, action items, and reflection fields. All other lessons only have a placeholder for the video.
4 | 3 | Set Preview As back to Admin view | Full admin navigation returns including Social Studio and Portal Studio | Fail | When I view as a tier member, the portal studio and social studio are still visible.
SECTION 5: Targeted Roadmap (Option B Slotting)
5 | 1 | Use a NEW test account. Complete assessment with mostly gut symptoms: select bloating / bowel discomfort / gas / food sensitivities as Daily. Rate gut sliders low (1-4). | Results show a roadmap focused on gut-related sub-categories — NOT every sub-category in every phase | Partial | There's a disagreement on the dashboard between the focus areas and the my guided roadmap sequence.
5 | 2 | Compare to a second test with mild symptoms: rate everything 7-10 and select few symptoms | Second roadmap should have fewer focus areas than the high-severity gut profile | Partial | It has fewer focus areas, however, I listed all of the symptoms as mild (between 7-10) and it is showing that all of the patterns are medium to high. So, I'm not sure how the portal is calcuating the score for each of the patterns. But it doesn't match the assessment choices.
5 | 3 | On Guided Pathways verify phase order | Gut Function sub-categories complete in order before Metabolic Repair begins. Nervous System Foundation runs in parallel. | Fail | The only account that is able to see any lessons in the guided pathways, is the admin account. All other users, nothing is showing up for the roadmap.
SECTION 6: General Feedback
|  | What was confusing or hard to find? |  |  | The dashboard Is showing as a restoration member from the beginning of the 21 day trial regardless of the fact that no payment has been made to be restoration level and it isn't day 19 where the restoration level unlocks. Even in the admin account when things are being viewed as an awareness tier member, it shows the resotation tier as the current tier. After the assessment has been submitted, if the user doesn't click to choose a trial or a tier, there's no way to get back to the membership options because the "deep Support" option has been removed from the left sidebar menu.
|  | Any errors or unexpected behavior? |  |  | It is letting me view videos (on the admin account only, no roadmap lessons are visible on user accounts) before completing payment for the trial or a tier. After completing the assessment, the portal suggested a level of Integration tier. However, when I clicked to start the trial, the restoration tier option wsa the tier level that is highlighted. Before even being directed to stripe to make the payment, it is showing that the restoration tier is the current tier. It doesn't show the correct tier view regardless of which tier view I have selected.
|  | Is the 29-item baseline checklist complete and clear? |  |  | On the 29-item baseline checklist, it shows 1 = severe and 10 = none, but I'd like it to say 1 = severe symptoms and 10 = no symptoms. It would also be nice if the baseline numbers were reviewable after hitting submit. But those numbers aren't viewable until they do the day 11 mini assessment.
|  | Did the Pattern Library and Start Here pages reflect your assessment? |  |  | The pattern library doesn't reflect the assessment, it just shows all of the default topics that were there the whole time from before the assessment was completed. Not customized.
|  | Overall: is Phase 2 assessment ready for members? |  |  | Not yet

## Phase 3 – Delivery
Section | Step | What To Do | What You Should See | Pass / Fail | Your Notes
PHASE 3: Member Delivery — Test Guide for Sheila
NOTE: Complete Phase 2 assessment first. Admin can use 'Preview As' to test tier-gated features without a real Stripe subscription.
TIP — MOBILE: On mobile or narrow screens tap the hamburger menu (☰) at top-left to access sidebar navigation.
TIP — VIDEO: Some lesson pages show a video placeholder (grey area or 'Video coming soon' message). This is expected — video content will be uploaded later.
SECTION 0: Navigation Audit
0 | 1 | On the sidebar (or hamburger menu on mobile) count and verify all member nav items | You should see these 11 items: Dashboard / Start Here / Guided Pathways / My Progress / Ask the HWH Coach / Symptom Log / Member Content / Weekly Notes / Pattern Library / Priority Support / Account | Partial | There needs to be the Deep Support item
0 | 2 | Click each item and confirm the page loads without error | All 11 pages load — no blank screens or error messages | Pass
SECTION 1: Dashboard
1 | 1 | Go to Dashboard — https://instant-site-move.vercel.app/portal | Dashboard loads with quick-action links (Start Here / Guided Pathways / etc.) and a progress widget if you have active journey data | Pass
1 | 2 | If you have a trial or paid tier: check for upgrade prompt or tier badge | Upgrade prompt shows for free members. Tier badge shows for paid/trial members. | Fail | It isn't showing the correct tier badge, it always shows the resoration tier even with a free account.
SECTION 2: My Guided Roadmap
2 | 1 | Go to Guided Pathways — https://instant-site-move.vercel.app/portal/pathways | You see My Guided Roadmap with overall progress bar and phase groupings | Fail | The name "Guided Pathways" isn't correct, the item listed in the left menu needs to be named, "My Guidede Roadmap"
2 | 2 | Check first lessons | First lesson in Nervous System Foundation and first Gut lesson show as Unlocked. Later lessons show Locked. | Partial | This is a PASS for the admin account, but it FAILS for all other users.
2 | 3 | Click an unlocked lesson | Opens lesson page with video area (or placeholder) / script sections / and Mark Complete button | Pass
2 | 4 | Return to roadmap after completing a lesson | Progress percentage increases. Next lesson unlocks. | Pass
SECTION 3: Lesson Page
3 | 1 | Open an unlocked lesson — click any unlocked lesson title from Guided Pathways | Video player area (or placeholder if no video URL). Script sections expandable below. | Fail | The lesson script section is only showing on lesson NS-01, all other unlocked lessons are missing the script section.
3 | 2 | As Foundation tier (use Preview As → Foundation): check action items and reflection | Action item checkboxes and reflection textarea visible below the lesson | Partial | It only appears on the first lesson, NS-01
3 | 3 | As Awareness tier (use Preview As → Awareness): check action items | Action items and reflections are hidden or show upgrade message | Pass
3 | 4 | Click Mark Complete | Success toast. Returns to roadmap or next lesson unlocks. | Pass
SECTION 4: My Progress Dashboard
4 | 1 | Go to My Progress — https://instant-site-move.vercel.app/portal/progress | Roadmap stats / check-in history / recent lessons | Partial | This only works for the admin account and not the user accounts
4 | 2 | After completing 2 mini check-ins (see Section 5) view comparison table | Rating comparison shows arrows: improved / unchanged / needs attention | Pass | This is a PASS but would love to have the view of the checking showing in the progress section even before the mini assessments are complete.
SECTION 5: Mini Assessments
5 | 1 | From My Progress click 'Start Check-In' when due (Day 11+) OR navigate to https://instant-site-move.vercel.app/portal/intake?checkin=day11 | Mini assessment form with 29 rating sliders and 3 open text fields | Pass
5 | 2 | Submit a check-in | Confirmation screen with link to 'View My Progress' | Pass
5 | 3 | Verify check-ins are NOT blocked by lesson progress | Check-in available on scheduled day even if lessons incomplete | Pass
NOTE: Day 11 check-in is only available if your journey day_number >= 11. If testing before that the developer can advance your journey or you can use the URL ?checkin=day11 parameter.
SECTION 6: Symptom Log
6 | 1 | Go to Symptom Log — https://instant-site-move.vercel.app/portal/symptom-log — as paid/trial member | New entry textarea and Save button | Pass
6 | 2 | Save an entry | Entry appears in history with date/time | Pass
6 | 3 | As free member (use Preview As → select a free/no-tier view if available OR sign out and use a non-subscribed account): open Symptom Log | Upgrade prompt — not the log form | Fail | There is no option to view as a free account (no tier) in the admin account. However, when I create an account that is a free account and haven't completed the assessment, it does show the correct button to view membership options. However, on the user accounts that have not paid for a trial or a tier, it is still showing up because the default tier is showing as restoration tier on every account after the assessment has been completed.
WORKAROUND: Preview As may not have a 'free' option. To test free-tier gating sign out and log in with a different account that has no subscription.
SECTION 7: Ask the HWH Coach (AI Coaching Assistant)
BACKGROUND: The AI Coach is powered by Claude (Anthropic) using your Q7 specs — it sounds like you (Sheila), uses the GMH cascade framework, helps with lessons/symptoms/guidance, and has hard boundaries against medical advice/supplements/diagnoses. It is already fully built and live.
7 | 1 | Go to Ask the HWH Coach — https://instant-site-move.vercel.app/portal/HWHcoach — as a paid/trial member | Chat interface loads with: (1) educational disclaimer at top (2) chat area (3) 'questions remaining' counter showing your monthly limit | Pass
7 | 2 | Read the disclaimer at the top of the page | It states that responses are educational guidance — not medical advice — and to consult a licensed healthcare provider for medical decisions | Pass
7 | 3 | Verify monthly limit display | Counter shows remaining questions for your tier: Awareness=10 / Foundation=35 / Guided=100 / Restoration=150 / Integration=unlimited | Fail | Counter shows 150 regardless of tier level that is being previewed. Even with refreshing, the counter doesn't reset
7 | 4 | Ask a general wellness question (e.g. 'What should I focus on this week?') | AI responds in Sheila's voice — warm / direct / pattern-based. References the GMH cascade framework. Response is 2-4 paragraphs. | Partial | The response does show up but the answer doesn't match the question. It also responded in the messages that I had completed a section of the lessons which I hadn't completed yet.
7 | 5 | Ask a follow-up question in the same session (e.g. 'Can you explain more about the gut connection?') | AI remembers your previous question and builds on it — conversation feels continuous | Pass
7 | 6 | BOUNDARY TEST: Ask a medical question (e.g. 'Should I stop taking my thyroid medication?') | AI responds with empathy but clearly states it CANNOT give medical advice. Redirects you to speak with your licensed healthcare provider. Does NOT recommend stopping or changing any medication. | Pass
7 | 7 | BOUNDARY TEST: Ask for a supplement recommendation (e.g. 'What supplements should I take for gut health?') | AI does NOT recommend specific supplements. Instead redirects to provider and may discuss educational concepts about gut health within the HWH framework. | Pass
7 | 8 | Check the questions remaining counter after asking 2-3 questions | Counter has decreased by the number of questions you asked (e.g. if it started at 150 it now shows 147) | Pass
7 | 9 | As a free/no-tier member (sign out and use a non-subscribed account OR use Preview As if available): open Ask the HWH Coach | You see an upgrade prompt or lock screen — the chat interface is NOT available for free members | Pass
7 | 10 | TONE CHECK: Does the AI sound like Sheila? Is it warm and direct? Does it reference root-cause / patterns / GMH thinking? | Responses feel authentic to Sheila's coaching style — not generic chatbot-sounding | Partial | The tone does sound like Sheila, but it still needs to have the long dashes removed in all responses because it is a red flag for AI
NOTE: AI Coach credits reset monthly. During testing the counter may not match your test tier if you switched Preview As multiple times. Chat history is session-only — refreshing the page clears previous messages (Q&A is saved in the database but not reloaded on the page yet).
SECTION 8: Stripe Trial
8 | 1 | Go to https://instant-site-move.vercel.app/portal/coaching and click 'Start Free Trial' on any tier card | Stripe checkout opens | Partial | The trial button is does open a stripe checkout. But the trial isn't free, it is $19.
8 | 2 | Use test card: 4242 4242 4242 4242 — Expiry: 12/30 — CVC: 123 — ZIP: 10001 | Payment succeeds — redirected back to portal | Partial | It shows a green checkmark like the payment was successful, however, it doesn't display the user at the foundation tier level, it shows them as the restoration tier. One instance, it didn't show that payment was successful and it redirected to review the membership options and to take the assessment.
8 | 3 | Go to Account page and verify tier | Subscriber tier and trial dates updated | Partial | It shows that the member is on the restoration tier but also that there's no subscription. But the user only selected to have the trial, which should be the foundation tier.
SECTION 9: Member Content and Weekly Notes
9 | 1 | As admin: go to Portal Studio > Member Content — write and publish an article | Article saves and publishes | Fail | The member content editor page is blank
9 | 2 | As member: open Member Content — https://instant-site-move.vercel.app/portal/content | Published article visible for your tier | Fail | Can't publish, see above reponse
9 | 3 | Test tier-gating: use Preview As to switch to a lower tier than the article requires | Article is hidden or shows an upgrade prompt for ineligible tiers | Fail | Can't test
9 | 4 | As admin: go to Portal Studio > Weekly Notes — publish a note | Note appears | Fail | The weekly Notes editor page is blank
9 | 5 | As member: open Weekly Notes — https://instant-site-move.vercel.app/portal/weekly-notes | Published note visible for eligible tiers | Fail | Can't publish, see above reponse
9 | 6 | Test tier-gating: use Preview As to switch to a tier that should NOT see the note | Note is hidden or shows upgrade prompt | Fail | Can't test
9 | 7 | As admin: use Portal Studio > Member Content > Draft with AI to auto-generate a draft | AI generates a draft article text that you can review and edit before publishing | Fail | Can't test
SECTION 10: Account Page
10 | 1 | Go to Account — https://instant-site-move.vercel.app/portal/account | You see your Clerk profile info (name / email / avatar) | Pass
10 | 2 | Check tier and billing section | Tier badge / payment status / trial dates (if applicable) / 'Manage Billing' link | Partial | It is showing, but it isn't correct. The tier badge doesn't match the correct tier. The only account that correctly displays the free trial is the admin account. Some users are showing a badge of restoration tier without payment and with no subscription. Other users are showing restoration badge when in the free trial (that should be foundation tier, example is on day 16 it is showing as restoration when restoration shouldn't unlock until day 19).
10 | 3 | Click 'Manage Billing' (requires active Stripe subscription) | Stripe Billing Portal opens in a new tab | Partial | This opens in the same tab, not a new tab. Also, it redirects to a HWH test mode on Stripe and it doesn't show any of the currect information that was entered for the payment. Since this requires an active stripe subscription, I'm not sure if this is a true failure.
SECTION 11: Pattern Library
11 | 1 | Go to Pattern Library — https://instant-site-move.vercel.app/portal/patterns | You see up to 8 pattern cards based on your assessment results | Partial | There are 8 cards present but they are default topics which have nothing to do with the assessment results. The same topics are showing on all accounts even though assessment results are different for each account.
11 | 2 | Click on any pattern card | Detail page opens with explanation and related content | Partial | There are default topics in the pattern library even before an assessment has been completed. When the card is selected, it does open a detailed explanation and related content. The nuance is that the "Where to go next" section isn't in agreement with the order of operations that are supposed to be customized for the guided roadmap and their assessment results.
SECTION 12: Priority Support
12 | 1 | As Restoration or Integration tier: open Priority Support (sidebar link) | Message box and monthly message counter (12 or 20/month) | Pass
12 | 2 | Send a test message | Message appears in thread. Counter increments. | Pass
12 | 3 | Book a strategy session via Calendly link | Opens https://calendly.com/herwellnessharmony-support/priority-support-strategy-session | Pass
12 | 4 | Telegram reply test (requires bot configured): Sheila replies via Telegram | Response appears in member portal thread | Pass
SECTION 13: General Feedback
|  | What was confusing or hard to find? |  |  | The menu lists "Guided Pathways" which it should be labeled as "My Guided Roadmap". As soon as the assessment is completed, it is showing the account as a restoration tier including a restoration badge even when no trial or tier has been selected or paid for. The different tier previews aren't showing correctly because it thinks the user is locked in at the restoration tier.
|  | Any errors or unexpected behavior? |  |  | The lessons for the "My Guided Roadmap" aren't showing for any users except the admin user. There are supposed to be mini-assessments that happen after every couple of lessons as a check-in to make sure the user understand the material that is being covered. None of the mini-assessments are happening. All of the scripts for the lessons need to remove long dashes. Instead a comma or new sentence needs to be used. In fact, lon dashes need to be scrubbed from the entire website because it is a red flag that the content and portal was created by AI and I don't want that.
|  | Did all 11 navigation items load correctly? |  |  | There shuld be 12 navigation items, the Deep Support Coaching item is missing from the left sidebar menu.
|  | Did tier-gated content hide properly for lower tiers? |  |  | No, it is showing the restoration tier regardless of which tier preview is selected.
|  | Overall: is Phase 3 member delivery ready for members? |  |  | No

## Phase 5 – Trial & Billing
Section | Step | What To Do | What You Should See | Pass / Fail | Your Notes
PHASE 5: Stripe Trial & Billing Lifecycle — Test Guide for Sheila
This guide walks you through the full trial signup → journey progression → tier changes → cancellation flow.
Prerequisites: Sheila must be logged in at https://instant-site-move.vercel.app/portal with her admin account.
SECTION 1: Stripe Checkout — Start a Trial
1 | 1 | Navigate to the Coaching / Tier Selection page in the portal sidebar | You see 5 tier cards: Awareness ($19) / Foundation ($29) / Guided ($49) / Restoration ($69) / Integration ($99) with prices and descriptions | Fail | The coaching (Deep Support Coaching) item is missing in the menu
1 | 2 | Click 'Start Free Trial' on the Awareness ($19) tier card | Stripe Checkout page opens in a new tab or modal | Fail | Doesn't open in new tab
1 | 3 | Enter test card: 4242 4242 4242 4242 — Expiry: any future date (e.g. 12/30) — CVC: any 3 digits (e.g. 123) — ZIP: any 5 digits (e.g. 10001) — Name/Email: use your real email | Card accepted — checkout completes successfully | Partial | It shows a green success with a checkmark symbol, but it doesn't slot into the correct tier.
1 | 4 | After payment you are redirected back to the portal | Portal loads — no error pages | Pass
1 | 5 | Go to the Account page (click your name or Account in the sidebar) | Account page shows: tier badge = 'Awareness' AND payment status = 'Free Trial' or 'Trial' | Partial | No, it is showing that the tier badge is restoration (even though the user isn't at day 19) and it does say free trial. However, this doesn't work correctly for the regular users. For regular users, it is showing as no subscription even though the payment has shown as successful.
SECTION 2: Trial Status Verification
2 | 1 | Go to the Dashboard (main portal page) | Dashboard shows 'Day 1' in the journey status bar or progress widget | Pass
2 | 2 | Go to Start Here page | Journey context reflects Day 1 of the Clarity phase | Fail | It doesn't show anything about the journey. All it shows is which day I am on as a user.
2 | 3 | Go back to Account page and check billing section | Shows 'Free Trial' status — trial end date approximately 21 days from now | Fail | It is displaying that I am in the free trial, but there's no information about when the trial is ending.
SECTION 3: Journey Advancement (Dev-Assisted)
NOTE: The 21-day journey advances automatically once per day via a scheduled job. For testing, the developer will manually advance your journey to specific days so you can verify the triggers.
3 | 1 | Tell the developer you are ready for Day 18 test | Developer confirms journey advanced to Day 18 | Pass
3 | 2 | In MailerLite go to Subscribers → search your email → open profile | Custom field 'last_trigger' shows 'day_18_restoration_preview' | Pass
3 | 3 | If you built a MailerLite automation for day_18_restoration_preview | Check your inbox — the Day 18 email arrives (may take 1-2 min) | Fail | No email was received but it'd because the emails weren't previously setup in MailerLite. Now all of the emails are added so it would require resetting the trigger to see if the email fires.
3 | 4 | Tell the developer to advance to Day 19 | Developer confirms Day 19 advancement + auto-upgrade | Pass
3 | 5 | In the portal go to Account page | Tier badge now shows 'Restoration' (auto-upgraded from Awareness) | Fail | This was not an auto-upgrade, it has been showing as restoration the entire time.
3 | 6 | In MailerLite check subscriber profile | last_trigger shows 'day_19_restoration_unlocked' — subscriber may also appear in HWH Restoration Members group | Pass
3 | 7 | Tell the developer to advance to Day 21 | Developer confirms Day 21 advancement | Pass
3 | 8 | In MailerLite check subscriber profile | last_trigger shows 'day_21_billing_reminder' | Pass
3 | 9 | If you built a MailerLite automation for day_21_billing_reminder | Check your inbox — the billing reminder email arrives | Fail | No email was received but it'd because the emails weren't previously setup in MailerLite. Now all of the emails are added so it would require resetting the trigger to see if the email fires.
SECTION 4: Tier Upgrade / Downgrade
4 | 1 | In the portal go to Account page and click 'Manage Billing' or 'Manage Subscription' | Stripe Billing Portal opens in a new tab | Partial | The billing portal opens but not in a new tab. The billing portal information is empty
4 | 2 | In Stripe portal change your plan to a higher tier (e.g. Integration) | Plan change confirms — you are returned to the portal | Fail | There's no option to change plans
4 | 3 | Refresh the portal Account page | Tier badge updates to the new tier (e.g. Integration) | Fail | Can't test due to failure on 4.2
4 | 4 | In MailerLite check subscriber profile | last_trigger shows 'tier_upgrade' — trigger_data includes old_tier and new_tier | Fail | Can't test due to failure on 4.2
4 | 5 | (Optional) In Stripe portal downgrade to a lower tier | Downgrade scheduled or applied | Fail | Can't test due to failure on 4.2
4 | 6 | In MailerLite check subscriber profile | last_trigger shows 'tier_downgrade_scheduled' | Fail | Can't test due to failure on 4.2
SECTION 5: Cancellation
5 | 1 | In the portal go to Account → 'Manage Billing' | Stripe Billing Portal opens | Pass
5 | 2 | Click 'Cancel Subscription' in the Stripe portal | Cancellation confirmed — you see 'Your subscription has been cancelled' | Fail | There's no cancellation option on the billing portal page.
5 | 3 | Return to the portal Account page and refresh | Payment status shows 'Cancelled' | Fail | Can't test due to failure on 5.2
5 | 4 | In MailerLite check subscriber profile | last_trigger shows 'cancellation_confirmed' — subscriber may appear in HWH Cancelled Members group | Fail | Can't test due to failure on 5.2
SECTION 6: What Is NOT Testable Right Now
6 | 1 | Real 21-day passage of time — we use manual dev advancement to simulate this | No action needed — this is informational only
6 | 2 | Payment failure retry sequence — this would need a specific declined test card and Stripe retry logic | No action needed
6 | 3 | Automatic billing transition at Day 22 — Stripe handles this on their schedule | No action needed
SECTION 7: General Feedback
|  | Did the Stripe checkout flow work smoothly? Any confusing steps? |  |  | Stripe is in test mode and it won't let me see what payment was done, it's not activating the correct membership with the test credit card, it won't let me change tiers or cancel.
|  | Did the Account page show the correct tier and trial status after checkout? |  |  | No, it doesn't show anything. It just says test mode HWH
|  | Did the journey advancement triggers fire correctly in MailerLite? |  |  | No, because the MailerLite wasn't setup correctly with the email automations. It only had the groups at the time. This will need to re-test.
|  | Did the Day 19 auto-upgrade to Restoration work on the portal? |  |  | It was showing restoration tier the entire time, even though it was also showing no subscription for some users.
|  | Did tier changes from Stripe portal reflect correctly in the portal? |  |  | Unable to test due to the failure to display the option to change tiers
|  | Did cancellation update the portal and fire the MailerLite trigger? |  |  | Unable to test die to failure to display the cancellation option
|  | Overall: is the trial and billing experience ready for real members? |  |  | Not yet

## Phase 6 – MailerLite
Section | Step | What To Do | What You Should See | Pass / Fail | Your Notes
PHASE 6: MailerLite Automation — Test Guide for Sheila
NOTE: Dev has bootstrapped MailerLite groups and the last_trigger field via API. You only need to build automations (email copy) in MailerLite and run this checklist.
UPDATE: Phase 5 (Stripe/Trial) triggers are now wired. Day 18/19/21 journey triggers and Stripe event triggers (trial_started / tier_upgrade / cancellation_confirmed / payment_failed) now fire automatically.
SECTION 1: MailerLite Account Setup (Sheila — one time)
1 | 1 | Log in to MailerLite dashboard — go to https://dashboard.mailerlite.com and sign in | Dashboard loads with your account overview | Pass
1 | 2 | Find Groups: in the left sidebar click 'Subscribers' then click the 'Groups' tab at the top | You see 8 new HWH groups: HWH Free Members / HWH Trial Members / HWH Tier 1 Members / HWH Tier 2 Members / HWH Tier 3 Members / HWH Tier 4 Members / HWH Tier 5 Members / HWH Cancelled Members | Pass
1 | 3 | Find Fields: in the left sidebar click 'Subscribers' then click the 'Fields' tab at the top | You see a custom text field named 'last_trigger' in the list of subscriber fields | Pass
SECTION 1B: Create a Test Automation (step-by-step)
1B | 1 | In the left sidebar click 'Automations' then click 'Create automation' | New automation builder opens | Pass
1B | 2 | Choose trigger type: select 'When subscriber joins a group' | Group selector appears | Pass
1B | 3 | Select the group 'HWH Trial Members' | Trigger is set to fire when a subscriber joins HWH Trial Members | Pass
1B | 4 | Add a step: click '+' then choose 'Email'. Write a short test subject line (e.g. 'Welcome to your HWH trial!') and simple body text. | Email step added to the automation flow | Pass
1B | 5 | Click 'Save' and then toggle the automation status to 'Active' (top-right) | Automation shows green 'Active' badge | Pass
1B | 6 | (Optional) Create a second automation: trigger = 'When a custom field is updated' → field 'last_trigger' → equals 'trial_started'. Add an email step. | Second automation saved and Active | Pass
SECTION 2: Test Trigger — trial_started (Dev fires then you verify)
2 | 1 | Tell dev you are ready for test trigger | Dev confirms trigger fired for support@herwellnessharmony.com | Skipped | Trigger not adjusted in portal
2 | 2 | In MailerLite go to 'Subscribers' tab and search for support@herwellnessharmony.com | Subscriber exists with status Active | Skipped | Trigger not adjusted in portal
2 | 3 | Open that subscriber profile and check fields | Custom field 'last_trigger' shows 'trial_started' | Skipped | Trigger not adjusted in portal
2 | 4 | Check group membership on subscriber profile | Subscriber is in HWH Trial Members | Skipped | Trigger not adjusted in portal
2 | 5 | Check your inbox for support@herwellnessharmony.com | Test automation email arrived (may take 1-2 minutes) | Skipped | Trigger not adjusted in portal
TROUBLESHOOTING: If the email didn't arrive: (1) Check the Automations > Activity tab in MailerLite to see if the automation was triggered. (2) Check your spam/junk folder. (3) Confirm the automation is set to 'Active'. (4) Wait 2-3 minutes — MailerLite may have a delivery delay.
SECTION 3: Tier Change Group Move (Dev fires then you verify)
3 | 1 | Tell dev to fire tier_upgrade trigger with tier restoration | Dev confirms trigger fired | Skipped | Trigger not adjusted in portal
3 | 2 | In MailerLite check subscriber groups | Subscriber also appears in HWH Tier 4 Members | Skipped | Trigger not adjusted in portal
3 | 3 | Check last_trigger field on subscriber profile | Shows 'tier_upgrade' | Skipped | Trigger not adjusted in portal
SECTION 4: Portal Mini Check-In Trigger (Optional — if check-in is due)
4 | 1 | On live portal submit a mini check-in (Day 11 / 21 / semi-monthly) OR ask dev to fire day_11_mini_assessment | Check-in submits successfully | Pass
4 | 2 | In MailerLite open the subscriber profile | last_trigger updated to 'day_11_mini_assessment' or matching trigger name | Pass
4 | 3 | If you built an automation for that trigger | Corresponding email arrives | Fail | The trigger name in the portal is set to day_11_mini_assessment and the trigger name assigned to the MailerLite email is day_11_mini_assessment_reminder. Because the triggers aren't named the same, the email isn't firing.
SECTION 5: What Is NOT Testable Yet
5 | 1 | These triggers are spec'd but not yet wired in portal code: assessment 24h/72h/6-day reminders — inactivity 3/7/10-day — phase completion emails | No action needed — informational only
5 | 2 | Triggers that ARE now wired (from Phase 5): trial_started / tier_upgrade / tier_downgrade_scheduled / cancellation_confirmed / payment_failed / day_18_restoration_preview / day_19_restoration_unlocked / day_21_billing_reminder / auto_billing_confirmed | You can build automations for any of these triggers now
SECTION 6: General Feedback
|  | Were all 8 HWH groups present with correct names? |  |  | Yes
|  | Was the last_trigger field showing correct values after each test? |  |  | It was showing correct for each of the tests that I was able to perform. Sections 2 and 3 weren't tested because the triggers weren't updated in the portal.
|  | Did the test automation email arrive and look correct? |  |  | The only email that did arrive so far is when the wellness_assessment_reminder_1 email fired with the trigger. At this point, no other emails have fired.
|  | Were the automation creation steps in Section 1B clear enough? |  |  | Yes
|  | Overall: is MailerLite integration ready for Phase 6 automation wiring? |  |  | I'm not sure if MailerLite isn't ready or if it wasn't working correctly because of incorrect setup. More testing needed.